## General info
Timeline/To-do |  |  |  | Jury |  | Mentor pairs
Action | Due date | Done | Additonal comments | Name #1 | FALSE | Name #1 | FALSE
Hacakthon date and topic agreed |  | FALSE |  | Name #2 | FALSE | Name #2 | FALSE
Agenda set |  | FALSE |  | Name #3 | FALSE | Name #3 | FALSE
Budget agreed |  | FALSE |  | Name #4 | FALSE | Name #4 | FALSE
Jury formed |  | FALSE |  | Name #5 | FALSE | Name #5 | FALSE
Mentors agreed |  | FALSE |  |  |  | Name #6 | FALSE
Hackathon announced |  | FALSE
Promotion plan in place |  | FALSE
Information about the hackathon up to date |  | FALSE |  | Council
Swag design requested and agreed |  | FALSE |  | Infra - Name #1 | FALSE
Swag ordered (t-shirts, stickers, ...) |  | FALSE |  | Design - Name #2 | FALSE
Jury and mentor guidelines updated |  | FALSE |  | Security - Name #3 | FALSE
Kick-off presentation/keynote |  | FALSE |  |  | FALSE
To-do list for the pitches |  | FALSE
Jury evaluation sheet updated |  | FALSE
Start gathering ideas for the hackathon |  | FALSE
Food ordered (cake, snacks, redbulls, ...) |  | FALSE |  | To use this template, please make a copy by clicking File -> Make a Copy. Then you can add whatever edits you want to.
Jury Slack channel created + info shared |  | FALSE
Mentors Slack channel created + info shared |  | FALSE
Promotion plan
Announcement | 12.12.2024 | FALSE
Opening slide with visual and date |  | FALSE
Announce the ideas board and updated information |  | FALSE
Ask team leads to encourage people to join the hackathon |  | FALSE
Share in Slack some tips and tricks how to generate hackathon ideas (brainstormings, chatGPT, ...) |  | FALSE
Facilitate brainstorming sessions for the hackathon |  | FALSE

## To-do list for the hackathon we
Detailed to-do list for the hackathon week
Zoom/Google Meet link added to the event | Monday | FALSE
Swag distributed (t-shirts, stickers, ...) | Monday | FALSE
Last minute drinks and snacks ordered | Monday | FALSE
| Monday | FALSE
| Monday | FALSE
| Monday | FALSE
Opening keynote ready | Tuesday | FALSE
Slack channels for hackathon teams created | Tuesday | FALSE
Reach out to pitchers to make sure they have their pitches ready and if they need some additional info/help | Tuesday | FALSE
| Tuesday | FALSE
| Tuesday | FALSE
The place for the pitches is set up (chairs, microphones, ...) | Wednesday | FALSE
Timer ready for pitches (3min pitch + 2min Q&A) | Wednesday | FALSE
🔴 Record the pitch event! | Wednesday | FALSE
| Wednesday | FALSE
| Wednesday | FALSE
| Thursday | FALSE
| Thursday | FALSE
| Thursday | FALSE
| Thursday | FALSE
Demo keynote ready | Friday | FALSE
| Friday | FALSE
| Friday | FALSE
| Friday | FALSE

## Budget
| Details | Planned | Actual | Difference
Prizes | 1st place |  |  | 0
| 2nd place | 0 | 0 | 0
| 3rd place | 0 | 0 | 0
|  | 0 | 0 | 0
Food | Snacks and drinks | 0 | 0 | 0
| Cake | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
|  | 0 | 0 | 0
Swag | T-shirts | 0 | 0 | 0
| Stickers | 0 | 0 | 0
|  | 0 | 0 | 0
Total |  | 0 | 0 | 0
|  | Free budget | 0

## T-shirts and sizes
Shirt size | Count | Percentage | Total number of expected participants
XS |  |  | 50
S
M
L
XL
2XL
Total | 0 | 0%

## Evaluation criteria
Evaluation criteria | Description | 100%
Idea | 0 - 1 - 2 - 3 - 4 - 5 - | 25%
PoC readiness | 0 - 1 - 2 - 3 - 4 - 5 - | 35%
Biz model | 0 - 1 - 2 - 3 - 4 - 5 - | 30%
Pitch and Demo | 0 - 1 - 2 - 3 - 4 - 5 - | 10%

## Feedback for next time
Pitching event | Overall feedback
example text | example text
Demo event
example text